## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Communication | Lack of direction | NA |  |  |  |  | Whole Team |  | As of now team communication is in intact
Technology Competence | Not familiar with Kotlin | Some team members are new to Android applictation | 4 | 1 | 1 | 2*5*1=10 |  |  | Main Coding work will be taken care by Seema, Sandeep, Low impact will be distributed among rest |  | on going
Requirements | Database or local storage | Planning to use Room database , however just need to see how to handle secure data | 2 | 4 | 2 | 16 | Jake Stephens, Sandeep Agrawal,Seema Palora |  | Jake and Sandeep will discuss this |  | on going
Testing | Unit Tests | Jake is unsure how to exactly to write unit tests for Kotlin / Android application. | 1 | 1 | 1 | 25 | Jake Stephens |  | Jake and Sandeep will discuss this |  | on going
| End to End Tests | Jake is unsure how to go about making the end to end tests for an android device. | 1 | 1 | 3 | 75 | Jake Stephens |  | Jake and Sandeep will discuss this |  | On going
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*3*4=48 | team leader and all members | 2020-09-09 | Redefine the project scope if necessary, and assign the tasks to other team members. | one member dropped off | closed
| add new team members | NA
| Lack of motivation or responsibility | NA
Communication | duplicate work | NA
| worked on wrong components | NA
| useless work | NA
| inconsistent work | NA
Requirements | unclear requirements | NA
| scope creep | NA
| constant requirements changes | Chances that wires may be updated based on requirement change in next iteration | 2 | 2 | 1 | 4*4*1=8 | Sandeep,Seema, Jake,Yang |  | If any new fields are introduced in UI, it needs story update and test case update, We plan to make sure before dev work starts, UI is uptodate to avoid rework
Management | improper task assignments | NA
| improper planning | NA
| lack of management skills | NA
Design and implementation | Improper design | NA
| improper technology stack | NA
| Messy code | NA
Testing | Not enough testing | NA
Integration and deployment | Not enough time for integration and deployment | NA
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.